Introduction to Software Engineering

Weekly Status Report

The student team is required to complete the Weekly Status Report documentation for the assigned course project, following the attached template.

Software Engineering Department

Faculty of Information and Technology

University of Science

Table of Contents

Right-click here and choose “Update Field” to build the table of contents.

Weekly Status Report

# Objectives

This document focus on the following topics:

- Reporting weekly progress against the project plan

- Recording issues and risks

- Recording the weekly status meeting

# Submission

- One report per week, from week 2 to week 10 (9 reports). The team lead (or backup) is responsible.

- The team chooses its own weekly deadline (e.g., the day after the status meeting) and states it in PA1.

- Commit the report to the repository: /docs/management/weekly/W<week>-status.docx (or .md), e.g., W03-status.docx. Do not overwrite or rewrite earlier reports; the commit history is the evidence of timeliness.

- Reports are not submitted on Moodle. They are graded at the end of the course as part of the Teamwork & tool usage component (working process).

# Report Information

| Item | Value |
| --- | --- |
| Team | T01 |
| Week | 04 |
| Date of meeting | 28/10/2026 |
| Current phase / PA | PA2 |
| Prepared by | Lại Phan Nhật Nam |
| Overall status | Green |

## Task Status

| WBS / task | Owner | Planned finish | Status | % done | Notes |
| --- | --- | --- | --- | --- | --- |
| 2.1 Vision, refined for PA2 | Phạm Hoàng Khôi Nguyên | 24/10/2026 | Complete | 100 |  |
| 2.2.1 SRS: Must-have functional requirements | Phạm Hoàng Khôi Nguyên Nguyễn Hoàng Tiến | 28/10/2026 | Complete | 100 |  |
| 2.2.2 SRS: Other functional requirements | Phạm Hoàng Khôi Nguyên Nguyễn Hoàng Tiến | 28/10/2026 | Complete | 100 |  |
| 2.2.3 SRS: Non-functional requirements (Measurable) | Phạm Hoàng Khôi Nguyên Nguyễn Hoàng Tiến | 31/10/2026 | Complete | 100 |  |
| 2.2.4 SRS: Data entities | Phạm Hoàng Khôi Nguyên Nguyễn Hoàng Tiến | 31/10/2026 (moved to 08/11/2026) | Not started | 0 | Extended the deadline because the Team Lead forgot to put the task on the board. |
| 2.4.1 Mockups: Account screen (Starts after 2.1) | Trần Văn Nam Ngô Phúc Khang | 28/10/2026 | Complete | 100 |  |
| 2.4.2 Mockups: Group and invite screens (Includes QR join) | Trần Văn Nam Ngô Phúc Khang | 31/10/2026 | Complete | 100 |  |
| 2.4.3 Mockups: Expense screen | Trần Văn Nam Ngô Phúc Khang | 28/10/2026 | Complete | 100 |  |
| 7.1 Weekly status meeting | Lại Phan Nhật Nam | 28/10/2026 | Complete | 100 |  |
| 7.2 Weekly status report | Lại Phan Nhật Nam | 28/10/2026 | Complete | 100 |  |

## Plan for Next Week

| WBS / task | Owner | Planned finish |
| --- | --- | --- |
| 2.2.4 SRS: Data entities | Phạm Hoàng Khôi Nguyên | 08/11/2026 |
| 2.3.1 Use cases: Use case for the must-have requirements | Phạm Hoàng Khôi Nguyên | 30/10/2026 |
| 2.3.2 Use cases: Use case for other requirements | Nguyễn Hoàng Tiến | 30/10/2026 |
| 2.4.4 Mockup: Debt screen | Trần Văn Nam | 01/11/2026 |
| 2.5 Requirement review | Everyone | 03/11/2026 |
| 4.1 Test plan | Ngô Phúc Khang | 06/11/2026 |
| PA2: Complete section 4, 5.1 | Phạm Hoàng Khôi Nguyên | 30/10/2026 |
| PA2: Complete section 7 | Phạm Hoàng Khôi Nguyên | 02/11/2026 |
| PA2: Complete section 5.2 | Nguyễn Hoàng Tiến | 30/10/2026 |
| PA2: Complete section 6.2 | Nguyễn Hoàng Tiến | 31/10/2026 |
| PA2: Complete section 3, 5.3 | Nguyễn Hoàng Tiến | 01/11/2026 |
| PA2: Complete section 6.3 | Ngô Phúc Khang | 01/11/2026 |
| PA2: Complete section 5.4 – after section 5.1, 5.2, 5.3 completion – | Ngô Phúc Khang | 02/11/2026 |
| PA2: Complete section 6.1, 8 – after section 6.2, 6.3 completion – | Trần Văn Nam | 02/11/2026 |
| PA2: Complete section 2, 11 | Trần Văn Nam | 03/11/2026 |
| PA2: Complete section 9 | Lại Phan Nhật Nam | 02/11/2026 |
| PA2: Complete section 1, 10 | Lại Phan Nhật Nam | 03/11/2026 |
| PA2: Manage AI usage log | Trần Văn Nam | 03/11/2026 |
| PA2: Proof-read | Lại Phan Nhật Nam | 03/11/2026 |
| 7.2 Weekly status meeting | Lại Phan Nhật Nam | 04/11/2026 |
| 7.2 Weekly status report | Lại Phan Nhật Nam | 04/11/2026 |

## Issues and Risks

| ID | Description | Impact | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| W4-R0 | Other tasks may be missing from the board. | Hidden work, unreliable status and weaker evidence for the Teamwork grade. | Audit Jira against every row of the plan. Add missing tasks with an owner and a date. | Lại Phan Nhật Nam | 29/10/2026 |
| W4-R1 | The review (03/11) is one day before submission, and section 10 is due the same day. | Fixes made after the review cannot be recorded in section 10. | Record findings on 03/11, make fixes and finalize section 10 on 04/11. | Lại Phan Nhật Nam | 30/10/2026 |
| W4-R2 | Must-have use cases, section 4 and 5.1 are all due 30/10, two days from now. | If Nguyên slips, 6.2, 6.3, 6.1, 7 and 9 slip with him. | Freeze the use case list on 30/10 and use first drafts. Finish the specs through section 7 by 02/11. | Phạm Hoàng Khôi Nguyên | 30/10/2026 |
| W4-R3 | Sections 7, 9, 5.4, 6.1 and 8 all finish on 02/11, the day before the review. | No buffer. Late sections are reviewed as drafts. | Set a rule that unfinished sections on the morning of 03/11 are reviewed as drafts. | Lại Phan Nhật Nam | 02/11/2026 |

## Meeting Minutes

| Member | Present | Done since last meeting | Next | Blockers |
| --- | --- | --- | --- | --- |
| Lại Phan Nhật Nam | Yes | Monitor the Github repository, Jira task board. Approve work submission | Complete section 1, 2, 9, 10 in PA2 Arrange weekly status meeting Make weekly status report | Requirement review blocks section 10 completion |
| Phạm Hoàng Khôi Nguyên | Yes | Vision, refined for PA2 SRS: Must-have functional requirements SRS: Other functional requirements SRS: Non-functional requirements (Measurable) | SRS: Data entities Use cases: Use case for the must-have requirements Complete section 3, 4, 5.1, 7 in PA2 |  |
| Trần Văn Nam | Yes | Mockups: Account screen (Starts after 2.1) Mockups: Group and invite screens (Includes QR join) Mockups: Expense screen | Mockup: Debt screen Complete section 8, 11 in PA2 Manage AI usage log in PA2 | Use Case Diagram needs to wait for the actor and use case list details. |
| Nguyễn Hoàng Tiến | Yes | SRS: Must-have functional requirements SRS: Other functional requirements SRS: Non-functional requirements (Measurable) | Use cases: Use case for other requirements Complete section 5.2, 5.3 in PA2 |  |
| Ngô Phúc Khang | Yes | Mockups: Account screen (Starts after 2.1) Mockups: Group and invite screens (Includes QR join) Mockups: Expense screen | Test plan Complete section 5.4, 6 in PA2 | Must wait for use case analysis before making the actual list |

## Metrics

| Metric | This week | Total |
| --- | --- | --- |
| Tasks completed | 9 | 21 |
| Commits | 11 | 25 |
| Pull requests merged / reviewed | 4 | 4 |
| Open defects (PA5) | n/a | n/a |